## unitd - 49 block a ( structur
List: UNITD - 49 BLOCK A ( STRUCTURAL WORKS )
Project: Unitd Living Space |  |  | Revision: 1
Created by: Ragav B |  |  | List status: Active
Date: Tue 24 Dec, 2024 |  |  | Tags: PROJECTS
No. | Code | Title | Description | Status | Priority | Assignees | Locations | Due date | Comments | Created by | Created on | Image 1 | Image 2 | Image 3 | Image 4 | Image 5 | Image 6 | Image 7 | Image 8 | Image 9 | Image 10 | Image 11 | Image 12 | Image 13 | Image 14 | Image 15 | Image 16 | Image 17 | Image 18 | Image 19 | Image 20 | Image 21 | Image 22 | Image 23 | Image 24 | Image 25 | Image 26 | Image 27 | File
FOOTING WORKS-SET-1-30 NOS
1 | EXA | Footing -Marking for excavation |  | Complete | Not set | Gulshan |  | 2024-07-10 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image | A Block - Foundation Strl drawings-Model (1)
2 | YQB | Footing - Excavation |  | Complete | Not set | Gulshan |  | 2024-07-13 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image; Image 8: View image; Image 9: View image; Image 10: View image; Image 11: View image; Image 12: View image; Image 13: View image; Image 14: View image; Image 15: View image; Image 16: View image | Soil Excavation
3 | 1I1 | Footing - Earth Sectioning |  | Complete | Not set | Gulshan |  | 2024-07-12 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image
4 | 62X | Footing - ATT ( Stage - 1 ) |  | Complete | Not set | Gulshan |  | 2024-07-14 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image; Image 8: View image; Image 9: View image; Image 10: View image; Image 11: View image; Image 12: View image | ATT - Anti Termite Treatment (1)
5 | TI2 | Footing - Dust Filling |  | Complete | Not set | Gulshan |  | 2024-07-14 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image | Dust Filling
6 | 1NS | Footing - PCC |  | Complete | Not set | Gulshan |  | 2024-07-15 |  | Ragav B | 2024-07-10 07:31 | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | [10 empty] | A Block -PCC Dimension (1)
7 | LIK | Footing - Reinforcement Fabrication & Erection |  | Complete | Not set | Gulshan |  | 2024-07-16 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image; Image 8: View image; Image 9: View image; Image 10: View image; Image 11: View image; Image 12: View image; Image 13: View image
8 | XGO | Footing - Sides Shuttering |  | Complete | Not set | Gulshan |  | 2024-07-16 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image
9 | VXG | Footing - QC Inspection |  | Complete | Not set | John |  | 2024-07-17 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image
10 | CAZ | Footing - RCC Casting |  | Complete | Not set | Gulshan |  | 2024-07-18 |  | Ragav B | 2024-07-10 07:31 | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image
11 | 44N | Footing - Deshuttering |  | Complete | Not set | Gulshan |  | 2024-07-19 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image; Image 8: View image
12 | Q7X | Footing - Curing |  | Complete | Not set | Gulshan |  | 2024-07-19 | - Pcc curing (Sat 13 Jul, 2024) | Ragav B | 2024-07-10 07:31 | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image
13 | YUF | Structural consultant - Checking |  | Complete | Not set | - Gulshan - Guna Sekar Architect |  | 2024-07-13 10:19 |  | Ragav B | 2024-07-27 04:51 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image
14 | 0Z8 | Architect checking for column orientation |  | Complete | Not set |  |  | 2024-07-27 10:26 |  | Ragav B | 2024-07-27 04:59 | Image 1: View image; Image 2: View image; Image 3: View image | A BLOCK COLUMN-SITE CHECKED
COLUMNS BELOW PB-SET-1-30 NOS
15 | D8Q | Columns Below PB - Starter Marking & Casting |  | Complete | Not set | Gulshan |  | 2024-08-09 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image; Image 8: View image; Image 9: View image; Image 10: View image; Image 11: View image; Image 12: View image; Image 13: View image
16 | UBZ | Columns-Below PB - Reinforcement Erection |  | Complete | Not set | Gulshan |  | 2024-08-10 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image; Image 8: View image; Image 9: View image
17 | 0G6 | Columns -Below PB - Shuttering |  | Complete | Not set | Gulshan |  | 2024-08-11 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image; Image 8: View image; Image 9: View image; Image 10: View image; Image 11: View image; Image 12: View image
18 | 8KK | Columns -Below PB - QC Inspection | Grid B24,B22,A18,A20,B22 G22 | Complete | Not set | John |  | 2024-08-11 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image; Image 8: View image; Image 9: View image; Image 10: View image (11.07916,76.97691)
19 | VNU | Columns -Below PB - RCC Casting |  | Complete | Not set | Gulshan |  | 2024-08-12 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image
20 | CDZ | Columns- Below PB - Deshuttering |  | Complete | Not set | Gulshan |  | 2024-08-13 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image
21 | TJK | Columns -Below PB - Curing |  | Complete | Not set | Gulshan |  | 2024-08-13 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image; Image 8: View image; Image 9: View image; Image 10: View image; Image 11: View image; Image 12: View image
22 | FH2 | Columns -Below PB - Footing Refilling & Consolidation |  | Complete | Not set | Gulshan |  | 2024-08-15 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image; Image 8: View image; Image 9: View image; Image 10: View image; Image 11: View image; Image 12: View image; Image 13: View image
FOOTING WORKS-SET-2-51 NOS
23 | OTT | Footing -Marking for excavation |  | Complete | Not set | Gulshan |  | 2024-07-16 | - H to w grids excavation marking completed (Fri 19 Jul, 2024) | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image
24 | NSF | Footing - Excavation |  | Complete | Not set | Gulshan |  | 2024-07-17 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image
25 | SCP | Footing - Earth Sectioning |  | Complete | Not set | Gulshan |  | 2024-07-18 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image
26 | ZFC | Footing - ATT for Bottom & Sides |  | Complete | Not set | Gulshan |  | 2024-07-18 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image; Image 8: View image; Image 9: View image; Image 10: View image; Image 11: View image | Anti Termite
27 | 49J | Footing - Dust Filling |  | Complete | Not set | Gulshan |  | 2024-07-20 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image; Image 8: View image; Image 9: View image
28 | 8JD | Footing - PCC |  | Complete | Not set | Gulshan |  | 2024-07-20 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image; Image 8: View image; Image 9: View image; Image 10: View image; Image 11: View image; Image 12: View image; Image 13: View image; Image 14: View image; Image 15: View image
29 | KCA | Footing - Reinforcement Fabrication & Erection |  | Complete | Not set | Gulshan |  | 2024-07-21 | - The delay is due to unexpected rains for the past four days - Expected completion is 25th july (Mon 22 Jul, 2024) | Ragav B | 2024-07-10 07:31 | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image
30 | 574 | Footing - Sides Shuttering |  | Complete | Not set | Gulshan |  | 2024-07-22 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image; Image 8: View image; Image 9: View image; Image 10: View image; Image 11: View image
31 | IAJ | Footing - QC Inspection | R25,23 | Complete | Not set | John |  | 2024-07-22 | - Internal Cleaning and Footing level Marking required (Tue 23 Jul, 2024) - OK (Fri 26 Jul, 2024) | Ragav B | 2024-07-10 07:31 | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image (11.07968,76.97661) | View image (11.079,76.97683) | View image (11.07997,76.97763) | View image (11.07903,76.97681) | View image (11.08004,76.97746) | View image (11.07938,76.9781)
32 | U1U | Footing - RCC Casting |  | Complete | Not set | Gulshan |  | 2024-07-24 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image
33 | 93R | Footing - Deshuttering |  | Complete | Not set | Gulshan |  | 2024-07-25 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image
34 | OJA | Footing - Curing |  | Complete | Not set | Gulshan |  | 2024-07-25 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image
35 | PQN | Footing -Marking for excavation |  | Complete | Not set | Gulshan |  | 2024-07-20 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image
36 | PNU | Footing - Excavation |  | Complete | Not set | Gulshan |  | 2024-07-21 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image; Image 8: View image; Image 9: View image; Image 10: View image; Image 11: View image
37 | QVF | Footing - Earth Sectioning |  | Complete | Not set | Gulshan |  | 2024-07-22 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image; Image 8: View image
38 | ICX | Footing - ATT for Bottom & Sides |  | Complete | Not set | Gulshan |  | 2024-07-23 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image; Image 8: View image; Image 9: View image; Image 10: View image | Anti Termite
39 | C1X | Footing - Dust Filling |  | Complete | Not set | Gulshan |  | 2024-07-24 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image; Image 8: View image
40 | 658 | Footing - PCC |  | Complete | Not set | Gulshan |  | 2024-07-25 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image; Image 8: View image
41 | GEA | Footing - Reinforcement Fabrication & Erection |  | Complete | Not set | Gulshan |  | 2024-07-26 |  | Ragav B | 2024-07-10 07:31 | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image
42 | IW8 | Footing - Sides Shuttering |  | Complete | Not set | Gulshan |  | 2024-07-27 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image; Image 8: View image; Image 9: View image; Image 10: View image; Image 11: View image; Image 12: View image; Image 13: View image; Image 14: View image; Image 15: View image; Image 16: View image
43 | YGL | Footing - QC Inspection | Grid - G22,J24,B11,,C2 ,F2,B7,L1,,4 K5 R1,T1 ,V4,F1,B11 | Complete | Not set | John |  | 2024-07-27 |  | Ragav B | 2024-07-10 07:31 | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image (11.08005,76.97758) | View image (11.07942,76.97677) | View image | View image | View image | View image
44 | UGB | Footing - RCC Casting |  | Complete | Not set | Gulshan |  | 2024-07-28 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image; Image 8: View image; Image 9: View image; Image 10: View image; Image 11: View image; Image 12: View image; Image 13: View image; Image 14: View image; Image 15: View image | A BLOCK COLUMN-SITE CHECKED
45 | FIP | Footing - Deshuttering |  | Complete | Not set | Gulshan |  | 2024-07-29 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image
46 | HTK | Footing - Curing |  | Complete | Not set | Gulshan |  | 2024-07-29 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image; Image 8: View image; Image 9: View image; Image 10: View image; Image 11: View image; Image 12: View image
47 | YEP | Plumbing discussion as per revised levels |  | Complete | Not set | Guna Sekar Architect |  | 2024-08-06 12:27 | - Discussion closed on the following points. 1. Internal Driange Levels 2. Sump with numatic locations 3. Eco Stp additional pump requirements. 4. Rain water pit depth. 5. Recycled water storage - cleaning systems (Thu 08 Aug, 2024) | Ragav B | 2024-08-06 06:59 | Image 1: View image; Image 2: View image
CLOUMNS BELOW PB-SET-2-51 NOS
48 | Z3N | Columns Below PB - Starter Marking & Casting |  | Complete | Not set | Gulshan |  | 2024-08-12 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image
49 | WU9 | Columns-Below PB - Reinforcement Erection |  | Complete | Not set | Gulshan |  | 2024-08-15 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image
50 | FNG | Columns -Below PB - Shuttering |  | Complete | Not set | Gulshan |  | 2024-08-16 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image; Image 8: View image; Image 9: View image; Image 10: View image; Image 11: View image; Image 12: View image; Image 13: View image
51 | LO5 | Columns -Below PB - QC Inspection | Concrete cube casting | Complete | Not set | John |  | 2024-08-16 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image; Image 8: View image; Image 9: View image; Image 10: View image; Image 11: View image; Image 12: View image; Image 13: View image; Image 14: View image; Image 15: View image; Image 16: View image
52 | D0Q | Columns -Below PB - RCC Casting |  | Complete | Not set | Gulshan |  | 2024-08-17 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image; Image 8: View image; Image 9: View image; Image 10: View image
53 | 1X9 | Columns- Below PB - Deshuttering |  | Complete | Not set | Gulshan |  | 2024-08-18 | - Delay due to rain (Mon 19 Aug, 2024) | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image
54 | U63 | Columns -Below PB - Curing |  | Complete | Not set | Gulshan |  | 2024-08-18 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image
55 | 6OJ | Columns -Below PB - Footing Refilling & Consolidation |  | Complete | Not set | Gulshan |  | 2024-08-20 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image
PLINTH BEAM WORKS - SET 1
56 | 1SD | Plinth Beam-Earth Work Excavation |  | Complete | Not set | Gulshan |  | 2024-08-15 | - Excavation delay due to rain and earth Work stopped for 3 days while starting (Mon 19 Aug, 2024) | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image
57 | ST5 | Plinth Beam-Brick On Edge works/PCC |  | Complete | Not set | Gulshan |  | 2024-08-17 | - Delayed due to rain and 3 days JCB not worked .Plinth Beam Works will closed within Sept 5th (Mon 26 Aug, 2024) | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image
58 | 6LO | Plinth Beam-Reinforcement Fabrication & Erection |  | Complete | Not set | Gulshan |  | 2024-09-11 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image
59 | ID2 | Plinth Beam-Side Shuttering |  | Complete | Not set | Gulshan |  | 2024-09-11 | - Delayed due to rain and 3 days JCB not worked .Plinth Beam Works will closed within Sept 5th (Mon 26 Aug, 2024) - This is shuttering for PCC , This is not Plinth beam shuttering (Sat 31 Aug, 2024) | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image
60 | GG9 | Plinth Beam-QC Inspection |  | Complete | Not set | John |  | 2024-09-11 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image; Image 8: View image
61 | I02 | Plinth Beam- RCC Casting |  | Complete | Not set | Gulshan |  | 2024-09-12 | - Delayed due to rain and 3 days JCB not worked .Plinth Beam Works will closed within Sept 5th (Mon 26 Aug, 2024) | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image
62 | YXQ | Plinth Beam- Deshuttering |  | Complete | Not set | Gulshan |  | 2024-09-15 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image
63 | URX | Plinth Beam- Curing |  | Complete | Not set | Gulshan |  | 2024-09-18 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image
64 | 24I | ATT - Plinth Beam ( Stage - 2 ) |  | Complete | Not set | Gulshan |  | 2024-08-27 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image | Anti Termite
PLINTH BEAM WORKS - SET 2
65 | 7DC | Plinth Beam - PCC |  | Complete | High | Gulshan |  | 2024-09-03 10:02 |  | Ragav B | 2024-09-02 04:34 | Image 1: View image; Image 2: View image; Image 3: View image
66 | RZA | Plinth Beam - Reinforcement & Shuttering |  | Complete | High | Gulshan |  | 2024-09-15 10:03 |  | Ragav B | 2024-09-02 04:36 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image
67 | ST3 | Plinth Beam - Concreting |  | Complete | High | Gulshan |  | 2024-09-16 10:05 |  | Ragav B | 2024-09-02 04:37 | Image 1: View image; Image 2: View image; Image 3: View image
68 | 5CC | Plinth Beam - Bitumen Coating | Total 2 coats(1st coat Primer - Mixing 20% of Water with mix) and (2nd coat with direct coat ) Both coats should be perpendicular to each other. | Complete | Not set | Gulshan |  | 2024-09-20 09:51 |  | Ragav B | 2024-09-23 04:22 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image | Bitufix - Dr.Fixit
BASEMENT WORKS
69 | Y45 | Basement- Block works above PB to Floor level |  | Complete | Not set | Gulshan |  | 2024-09-30 | - Date Revised from 28th to 30th. Delay Due to level finalisation (Mon 30 Sep, 2024) | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image
70 | UPU | Basement- Earth Ramming & Compaction |  | Complete | Not set | Gulshan |  | 2024-10-25 | - Revised 28th September to 10th October . Delay due to plinth level finalisation (Mon 30 Sep, 2024) | Ragav B | 2024-07-10 07:31
71 | J7N | Basement- QC Inspection |  | Complete | Not set | John |  | 2024-10-26 |  | Ragav B | 2024-07-10 07:31
72 | 2VE | Plinth Level Confirmation |  | Complete | Not set | - Arun - GM - Projects - Gulshan - Guna Sekar Architect - John Diwagar - projectengineer@liveunitd.com |  | 2024-09-18 11:52 | - All Blocks Plinth Level and Water Slope for external area Finalisation (Mon 30 Sep, 2024) | Ragav B | 2024-09-30 06:28 | Image 1: View image; Image 2: View image | U 49 - Water Slope on drive way
73 | 46V | Plinth Beam - inside Plastering Works |  | Complete | Not set | - Gulshan - projectengineer@liveunitd.com |  | 2024-10-12 18:14 |  | Ragav B | 2024-10-03 12:47 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image | TDS-Conplast-WL-India33
STILT FLOOR-COLUMNS
74 | NOU | Stilt Floor - Column-Starter Marking & Casting |  | Complete | Not set | Gulshan |  | 2024-10-02 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image
75 | KUC | Stilt Floor - Column- Reinforcement Fabrication & Erection works |  | Complete | Not set | Gulshan |  | 2024-10-05 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image; Image 8: View image; Image 9: View image
76 | 2VY | Stilt Floor - Column-Shuttering works |  | Complete | Not set | Gulshan |  | 2024-10-08 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image; Image 8: View image; Image 9: View image
77 | AYQ | Stilt Floor - Column-QC Inspection |  | Complete | Not set | John |  | 2024-10-09 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image (11.0796,76.97701); Image 7: View image; Image 8: View image
78 | JKS | Stilt Floor - Column- RCC casting |  | Complete | Not set | Gulshan |  | 2024-10-10 | - Work completed (Sat 19 Oct, 2024) | Ragav B | 2024-07-10 07:31 | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image | View image
79 | V4B | Stilt Floor - Column- Deshuttering |  | Complete | Not set | Gulshan |  | 2024-10-11 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image
80 | NVU | Stilt Floor - Column- Curing |  | Complete | Not set | Gulshan |  | 2024-10-11 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image; Image 8: View image; Image 9: View image
STILT FLOOR-ROOF WORKS
81 | 7S1 | Stilt Floor -Roof Beam- Bottom Shuttering Works |  | Complete | Not set | Gulshan |  | 2024-11-02 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image
82 | IEP | Stilt Floor -Roof Beam- Inner Sides Shuttering Works |  | Complete | Not set | Gulshan |  | 2024-11-03 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image
83 | 7YX | Stilt Floor -Roof Slab- Shuttering Works |  | Complete | Not set | Gulshan |  | 2024-11-05 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image
84 | 7O3 | Stilt Floor -Roof Beam- Reinforcement Fabrication & Erection |  | Complete | Not set | Gulshan |  | 2024-11-07 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image
85 | 0HC | Stilt Floor -Roof Slabs- Reinforcement Fabrication & Erection |  | Complete | Not set | Gulshan |  | 2024-11-25 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image
86 | BKS | Stilt Floor -Roof Beams- Outer Shuttering Works |  | Complete | Not set | Gulshan |  | 2024-11-21 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image
87 | ZBC | Stilt Floor -Staircase Shuttering, Reinforcement works |  | Complete | Not set | Gulshan |  | 2024-11-15 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image
88 | ZH0 | Stilt Floor - QC Inspection works |  | Complete | Not set | John |  | 2024-11-27 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image; Image 8: View image; Image 9: View image; Image 10: View image; Image 11: View image; Image 12: View image; Image 13: View image; Image 14: View image; Image 15: View image; Image 16: View image
89 | KOL | Stilt Floor -Staircase RCC Casting works |  | Complete | Not set | Gulshan |  | 2024-11-29 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image
90 | LCP | Stilt Floor -QC & Structural Engineer, MEP Consultant Inspection works |  | Complete | Not set | Gulshan |  | 2024-11-28 | - Jhon - Please add the consultant Designation like - Structural consultant.Elec consultant in the Remarks notes sheets. Also i want them to visit after the completion of works, Elec consultant mentioned as there are few items were pending. These all to be documented. Cube test results to be attached here for future refrences. (Thu 28 Nov, 2024) - Sathish - Dont allow anyone inside site without helmets. (Thu 28 Nov, 2024) | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image (11.07901,76.9768); Image 6: View image; Image 7: View image; Image 8: View image; Image 9: View image
91 | X5L | Stilt Floor -Roof Slab & Beam MEP Conduit works |  | Complete | Not set | Gulshan |  | 2024-11-26 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image
92 | QXD | Stilt Floor -Roof Slab & Beam RCC casting works |  | Complete | Not set | Gulshan |  | 2024-11-29 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image; Image 8: View image; Image 9: View image; Image 10: View image
93 | DQK | Stilt Floor -Roof Slab & Beam Curing works |  | Complete | Not set | Gulshan |  | 2024-12-14 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image
94 | 74O | Stilt Floor -Roof Slab & Beam Outer Side Deshuttering works |  | In progress | Not set | Gulshan |  | 2024-12-07 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image
95 | 0JY | Stilt Floor -Roof Slab & Beam Bottom Deshuttering works |  | Complete | Not set | Gulshan |  | 2024-12-07 |  | Ragav B | 2024-07-10 07:31 | Image 1: View image; Image 2: View image; Image 3: View image
FIRST FLOOR-COLUMNS
96 | LPV | First Floor - Column-Starter Marking & Casting |  | Complete | Not set | Thirukumaran | Gulshan | 2024-12-03 |  | Ragav B | 2024-11-11 08:56 | Image 1: View image; Image 2: View image; Image 3: View image
97 | XRN | First Floor - Column- Reinforcement Fabrication & Erection works |  | Complete | Not set | Thirukumaran | Gulshan | 2024-12-05 |  | Ragav B | 2024-11-11 08:56 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image
98 | YV8 | First Floor - Column-Shuttering works |  | Complete | Not set | Thirukumaran | Gulshan | 2024-12-07 |  | Ragav B | 2024-11-11 08:56 | Image 1: View image; Image 2: View image; Image 3: View image
99 | N0Y | First Floor - Column-QC Inspection |  | Complete | Not set | Thirukumaran | Gulshan | 2024-12-07 |  | Ragav B | 2024-11-11 08:56 | Image 1: View image (11.07955,76.97648); Image 2: View image (11.07955,76.97648); Image 3: View image (11.07955,76.97647)
100 | 6RF | First Floor - Column- RCC casting |  | Complete | Not set | Thirukumaran | Gulshan | 2024-12-09 |  | Ragav B | 2024-11-11 08:56 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image; Image 5: View image; Image 6: View image; Image 7: View image
101 | 47C | First Floor - Column- Deshuttering |  | In progress | Not set | Thirukumaran | Gulshan | 2024-12-11 |  | Ragav B | 2024-11-11 08:56 | Image 1: View image; Image 2: View image
102 | Q6B | First Floor - Column- Curing |  | In progress | Not set | Thirukumaran | Gulshan | 2024-12-12 |  | Ragav B | 2024-11-11 08:56 | Image 1: View image
FIRST FLOOR-ROOF WORKS
103 | 5TU | First Floor -Roof Beam- Bottom Shuttering Works |  | In progress | Not set | Thirukumaran | Gulshan | 2024-12-18 |  | Ragav B | 2024-11-11 08:56 | Image 1: View image; Image 2: View image
104 | Z0T | First Floor -Roof Beam- Inner Sides Shuttering Works |  | Incomplete | Not set | Thirukumaran | Gulshan | 2024-12-18 |  | Ragav B | 2024-11-11 08:56
105 | 79N | First Floor -Roof Slab- Shuttering Works |  | In progress | Not set | Thirukumaran | Gulshan | 2024-12-18 |  | Ragav B | 2024-11-11 08:56 | Image 1: View image; Image 2: View image; Image 3: View image; Image 4: View image
106 | JSE | First Floor -Roof Beam- Reinforcement Fabrication & Erection |  | Incomplete | Not set | Thirukumaran | Gulshan | 2024-12-26 |  | Ragav B | 2024-11-11 08:56
107 | D72 | First Floor -Roof Slabs- Reinforcement Fabrication & Erection |  | Incomplete | Not set | Thirukumaran | Gulshan | 2024-12-25 |  | Ragav B | 2024-11-11 08:56
108 | LWL | First Floor -Roof Beams- Outer Shuttering Works |  | Incomplete | Not set | Thirukumaran | Gulshan | 2024-12-17 |  | Ragav B | 2024-11-11 08:56
109 | 8YP | First Floor -Staircase Shuttering, Reinforcement works |  | Incomplete | Not set | Thirukumaran | Gulshan | 2024-12-25 |  | Ragav B | 2024-11-11 08:56
110 | 3NG | First Floor -Staircase QC Inspection works |  | Incomplete | Not set | Thirukumaran | Gulshan | 2024-12-27 |  | Ragav B | 2024-11-11 08:56
111 | V90 | First Floor -Roof Slab & Beam MEP Conduit works |  | Incomplete | Not set | Thirukumaran | Gulshan | 2024-12-26 |  | Ragav B | 2024-11-11 08:56
112 | UA3 | First Floor -Staircase RCC Casting works |  | Incomplete | Not set | Thirukumaran | Gulshan | 2024-12-28 |  | Ragav B | 2024-11-11 08:56
113 | Z5Y | First Floor -Roof Slab & Beam RCC casting works |  | Incomplete | Not set | Thirukumaran | Gulshan | 2024-12-28 |  | Ragav B | 2024-11-11 08:56
114 | 45O | First Floor -QC & Structural Engineer, MEP Consultant Inspection works |  | Incomplete | Not set | Thirukumaran | Gulshan | 2024-12-27 |  | Ragav B | 2024-11-11 08:56